## Sheet1
Name	Week 7	Week 8	Week 9	Week 10	Week 11	Week 12	Week 13	Week 14	Week 15	Week 16	Week 17	Week 18	Week 19	Week 20	Week 21	Week 22
Daniel Mammone
Harley Tuleja
Mary Jane
Steven Flanigan
Liam Hackett

## Sheet2
Day	DATE	WORKLOAD		Completed
Monday	04/11/19	Polish team profile. With additions according to feedback / From A2 / Team name / Personal Information / Group Processes(New) / Career Plans(New)
Tuesday	05/11/19	Fix up our tools section according to A2 feedback. / Assign Workload For Project Description section of this / Report. / Start On Overview / TOPIC / MOTIVATION / LANDSCAPE / Decide how we are going to do our presentation
Wednesday	06/11/19	Polish OVERVIEW / Start on Detailed Description / AIMS / PLANS AND PROGRESS / ROLES
Thursday	07/11/19	Start on Overview / SCOPE AND LIMITS / TOOLS AND TECHNOLOGIES / Start on presentation idea.
Friday	08/11/19	Polish AIMS / PLANS AND PROGRESS / Tools AND TECHNOLOGIES
Saturday	09/11/19	If Keen it is a weekend after all / Start On / TESTING / TIMEFRAME / RISKS, GROUP PROCESSES AND COMMS
Sunday	10/11/19	Chill, play some games eat a pizza
Monday	11/11/19	POLISH REPORT SO FAR / Start On / TESTING / TIMEFRAME RISKS, / GROUP PROCESSES AND COMMS
Tuesday	12/11/19	Skills and jobs section start
Wednesday	13/11/19	Skills and jobs section polish
Thursday	14/11/19	Final Draft for report and final edits on Presentation.
Friday	15/11/19	More polish
Saturday	16/11/19	Submit ahead of time because we rock
Sunday	17/11/19	Party as this course is over